## Burndown Chart
Sprint Burndown Chart
Sprint 1
Task ID | Task Description | Initial Estimate | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Code Implementation | 0.5 | 0.35 |  | 0.15
2 | Update User Stories | 2 |  | 2
3 | Class Diagrams | 6 |  | 2 |  | 4
4 | Use Case Diagram | 6 |  | 2 |  | 2 | 2
5 | Sequence Diagram | 6 |  | 2 |  | 2 | 2
6 | Unit Tests | 12 |  | 4 |  | 4 | 4
7 | Reviews | 6 |  |  |  |  | 4
9 | Update the report | 12
Completed Effort |  | 0 | 0 | 12 | 0 | 12 | 12
Remaining Effort |  | 50 | 50 | 38 | 38 | 26 | 14
Ideal Burndown |  | 50 | 40 | 30 | 20 | 10 | 0