## Burndown Chart
Sprint Burndown Chart
Week 3
Task ID | Task Description | Initial Estimate | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Non-trivial design patterns identification | 12 |  | 1 | 0.5 | 1.5
2 | Codebase metrics assessment | 6 |  |  | 0.75
Completed Effort |  | 0 | 0 | 1 | 1.25 | 1.5 | 0
Remaining Effort |  | 18 | 18 | 17 | 15.75 | 14.25 | 14.25
Ideal Burndown |  | 18 | 14.4 | 10.8 | 7.2 | 3.6 | 0