## Burndown Chart
Sprint Burndown Chart
Sprint 1
Task ID | Task Description | Initial Estimate | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Code Implementation | 12 |  |  | 5 | 4 | 2.5
2 | Update User Stories | 3 |  |  | 1
3 | Class Diagrams | 6
4 | Use Case Diagram | 6
5 | Sequence Diagram | 6
6 | Unit Tests | 12
7 | Reviews | 6
9 | Update the report | 12
Completed Effort |  | 0 | 0 | 0 | 6 | 4 | 0
Remaining Effort |  | 63 | 63 | 63 | 57 | 53 | 53
Ideal Burndown |  | 63 | 50.4 | 37.8 | 25.2 | 12.6 | 0