## Burndown Chart
Sprint Burndown Chart
Sprint 1
Task ID | Task Description | Initial Estimate | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Review Design Patterns' assessment | 9 | 6 |  | 3
2 | Make Codebase Metrics | 3 | 1 |  | 2
3 | Review Codebase Metrics | 5 |  |  | 3 | 2
4 | Make Code Smells' assessment | 3 |  |  | 3
5 | Review Code Smells' assessment | 10 | 1 |  | 2 | 7
6 | Make Use Case Diagrams | 5 | 1 |  | 1 | 3
7 | Review Use Case Diagrams | 6 | 1 |  |  | 5
9 | Update the report | 6 |  |  | 1 | 1 | 4
Completed Effort |  | 0 | 10 | 0 | 15 | 18 | 4
Remaining Effort |  | 47 | 37 | 37 | 22 | 4 | 0
Ideal Burndown |  | 47 | 37.6 | 28.2 | 18.8 | 9.4 | 0